## Issue Register
SENA Prioritized Issue Register
v1.0 - 2026-07-07 - Evidence audited against the 2026-07-05 spec, the development plan, www.sena.hk, and the sena-hk-template repo. Effort: S <= 3 dev-days, M <= 2 dev-weeks, L > 2 dev-weeks.
ID | Issue | Severity | Evidence / Source | Why it matters | Affected module | Recommended fix | Effort | Within 3 months?
SENA-001 | Fusion view coordinates come from the jENA ENA-space projection with social arcs overlaid - not from A_fusion (the spec's 'projection error', Example 1) | Critical | Confirmed: lib/sena/layout.ts buildSenaEnaSpaceCoordinateMap (source: jena-js manifest points/nodePositions); CONTEXT.md 'A1 Inner Solid Mesh' grammar; plan G3 | Person-code distances on the canvas carry no analytical meaning; the platform's core scientific claim is invalid until coordinates are jointly estimated from A_fusion (spec Prop. 4) | M6 Embedding / Workspace UI | Build embedding service: Laplacian eigenmaps, classical MDS with Schoenberg check, commute-time; fusion view renders Z = Phi(A_fusion); keep overlay only as badged exploratory layout | L | Yes
SENA-002 | No embedding or eigendecomposition exists anywhere in the codebase; no Schoenberg check, no stress/strain, no commute-time | Critical | Confirmed: grep for eigen/schoenberg/commute/mds across lib+components = 0 hits | Prop. 5 exactness cannot be evaluated; cross-type distance claims cannot carry the required exact/approximate status | M6 Embedding | Implement SCHOENBERG_MDS + COMMUTE_TIME_EMBED + stress readout per plan A6; golden tests T10-T11 | L | Yes
SENA-003 | Directed data silently symmetrized by default (undirectedSocial: true; S[target][source] += weight on ingest); no directed fusion, no independent B_PC/B_CP | Critical | Confirmed: lib/sena/model.ts defaultOptions + buildSocialMatrix; plan G7 | Directed uptake/attention data is misrepresented; undirected theorems get applied to directed objects (plan A5 counterexample: min eig -0.218) | M1 Ingest / M2 Layers / M5 Operators | Preserve R; explicit direction config; directed operators (out/in-degree RW); symmetrization only as a declared, permanently badged choice; support B_CP upload | M | Yes
SENA-004 | Hard-coded undisclosed layer weights alpha=0.72, beta=0.64, gamma=0.86 with no derivation, disclosure, or sensitivity analysis | High | Confirmed: lib/sena/model.ts defaultOptions | Arbitrary constants steer every view; spec Cor. 2 makes weights meaningless without the declared normalization; no sensitivity = no defensible claims | M3/M4 + UI | Default to 1,1,1; move to config; disclose in model card with normalization rule; add (alpha,beta,gamma) sensitivity grid to nightly CI | S | Yes
SENA-005 | Normalization engine lacks admissibility axioms; 'none' rule allowed; Frobenius missing; no symmetry/nonnegativity/N(0)=0/positive-divisor assertions | High | Confirmed: lib/sena/model.ts normalizeMatrix; plan G8 | Axiom violations pass silently; alpha/beta/gamma meaning drifts across rules; Def. 4 is the foundation of layer comparability | M3 Normalization | Implement ADMISSIBLE_NORMALIZE per plan A2 (max, frobenius, log1p_max only); assert all five axioms; record divisors + scale-invariance flag in provenance; tests T14-T15 | S | Yes
SENA-006 | No isolated-vertex handling: no I0 registry, no V+ restriction, no zero-inverse or epsilon conventions for D^-1 operators | High | Confirmed: grep isolated/I0/zero-degree in lib/sena = 0 hits; plan G6 | Zero-degree nodes will crash or silently corrupt normalized operators; spec requires retention and declared conventions | M5 Operators + UI panel | DEGREES_AND_ISOLATED per plan A4; three conventions implemented + provenance; isolated-node UI panel (dimmed, never dropped); tests T4-T7 | M | Yes
SENA-007 | No golden regression fixtures: the worked example's numbers appear nowhere in the test suite | Critical | Confirmed: lib/sena/__tests__/sena.test.ts (4,986 lines) contains none of d=(2,2.25,1.25,...) or spectrum {0,0.88,1.88,2.61,3.31,3.81}; plan G2 | Any modification is unverifiable; the migration cannot start safely; this is the single cheapest highest-value fix | Testing / CI | Encode worked-example fixture + T1-T15 in week 1-2 (P0), run in expected-fail mode, burn down | S | Yes
SENA-008 | Test pyramid inverted: ~30 test files guard enterprise/auth/ops routes; math core has no fixture-based tests | High | Confirmed: lib/sena/__tests__ listing (scim, mfa, backup, go-live, alerts...) vs. no math goldens | Regression protection is concentrated exactly where correctness matters least for the research claims | Testing | Moratorium on new route tests until golden + unit math suites exist; CI gates per test strategy doc | M | Yes
SENA-009 | God component: components/sena/SenaFusionWorkspace.tsx is 10,860 lines; layout math lives in components (workspace/fusion-layout.ts) | High | Confirmed: wc -l = 10,860; fusion-layout.ts in components tree | Unreviewable, unmergeable, untestable; UI and math entangled blocks every subsequent fix | UI architecture | Decompose into <500-line components; move all computation into lib/ (or server); UI consumes typed view-models only | L | Yes (partial: extract compute paths first)
SENA-010 | Invented, undeclared metrics shown to users: conceptBrokerage = sum(w/(0.5+W_ab)) with magic 0.5; neighborContribution = S x B row products; z-scores mixed across types | High | Confirmed: lib/sena/model.ts buildMetrics | Unvalidated numbers presented as analytics; not in the spec; magic epsilon is an undeclared regularization; risks false role claims | M8 Typed centrality | Replace with spec's four typed families (S-block, W-block, B-bipartite, whole-graph typed with tag); if kept, label experimental + model-card entry + sensitivity | M | Yes
SENA-011 | Attribution deviates from spec: G built from stanza grouping (not G_i = X^T diag(Y_i) X); no normalized G_hat; 'contribution/contributes' wording is the default everywhere | High | Confirmed: lib/sena/model.ts buildPairContribution; fusion-math.ts notes ('explains who contributes'); CONTEXT.md defines G as 'contribution layer'; plan G5 | Overstates individual contribution (spec Example 4); G/G_hat identities are the spec's own audit mechanism and are absent | M7 Attribution | Implement A7: G_i = X^T diag(Y_i,:) X + G_hat with 0/0->0; identity tests T12-T13; wording gate: association/exposure unless X_ita present | M | Yes
SENA-012 | Bridge B silently mixes counts with AI coding confidence (B += segment.confidence ?? 1) - weighting rule undeclared | Medium | Confirmed: lib/sena/model.ts buildBridgeMatrix | Bridge semantics undefined; AI-reliability leaks into edge weights without disclosure; breaks reproducibility across coder configurations | M2 Layers | Make count-based vs confidence-weighted an explicit declared config; disclose in model card item 2; fixture for each | S | Yes
SENA-013 | API contract (60 resources / 94 methods) contains zero occurrences of fusion, alpha/beta/gamma, normalization, Laplacian, embedding, seed, isolated, directed | High | Confirmed: grep over the 93KB OpenAPI export at /api/sena/docs | The public contract cannot express the model's conventions; provenance and model cards cannot flow to clients or exports | API / M11 | Analysis API v2: config in, provenance envelope out on every response (see advisory report section 4); version via schema-registry | M | Yes
SENA-014 | Inverted API surface: analytical core is one monolithic /api/sena/analyze resource while 22 ops resources + SCIM/SSO/MFA/go-live/attestation surround it | High | Confirmed: /docs API table; repo lib/sena/* dominated by enterprise/ops modules | Maintenance surface vastly exceeds a small team's capacity; core analysis is under-specified while ceremony accumulates | Architecture | Freeze the enterprise/ops surface (change moratorium, no deletion needed); decompose analysis API along M1-M11 seams | M | Yes (freeze now, decompose through P1-P3)
SENA-015 | Legacy ENA engine publicly invokable without auth: POST /api/ena/run (group legacy-ena, auth: public) | Medium | Confirmed: /docs API table | Abuse/DoS vector; legacy June-11 semantics remain callable and can contradict the migrated engine | Security / API | Gate behind session auth or remove; publish deprecation date; redirect docs to v2 | S | Yes
SENA-016 | Legal/ethics pages are placeholders: Privacy, Terms, Security, Responsible AI links all point to /#docs anchors; site invites registration + discourse upload | High | Confirmed: footer links on every page fetched 2026-07-07 | A platform analyzing student discourse cannot invite uploads without a privacy policy, terms, and consent language; PDPO (HK) / IRB exposure | Product / Legal | Ship real Privacy, Terms, Security, Responsible-AI pages before any real-data beta; add consent + pseudonymization fields to dataset contract | S | Yes
SENA-017 | No reproducibility controls: no seed parameter anywhere in the analysis path; no dataset content-hash versioning | Medium | Confirmed: grep seed in lib/sena math path = 0 (excl. unrelated); no version hash on datasets | Stochastic steps (future embeddings, permutation tests) will be irreproducible; exports cannot be tied to inputs | M1-M11 | seed in AnalysisConfig threaded to all stochastic ops; dataset version = content hash; both in model card | S | Yes
SENA-018 | Marketing math contradicts the spec: /method shows 'SENA(t) = SNA(t) (+) ENA(t)' (a direct sum = block-diagonal = gamma 0 = no bridge); /platform Fusion Lab declares inputs 'ENA outputs + SNA outputs' | Medium | Confirmed: sena.hk/method and /platform fetched 2026-07-07 | The site's own copy describes the disconnected boundary case and the overlay pipeline the spec forbids; erodes credibility with exactly the reviewers SENA must convince | Content / Docs | Rewrite method/platform copy to the spec's blessed sentence (heterogeneous typed block-adjacency); Fusion Lab inputs become S, W, B layers | S | Yes
SENA-019 | Naming drift A_SENA vs A_fusion across code, docs and exports (plan G1); core lib uses A_fusion but export/report surfaces inconsistent | Medium | Plan G1 (team-documented); repo core confirmed A_fusion | Broken traceability between paper, code, UI and exports; reviewer confusion | All modules | Single-name sweep + lint ban on A_SENA; rename in API labels, UI, exported reports | S | Yes
SENA-020 | Temporal comparisons without declared normalization policy or significance testing; no permutation/bootstrap tooling anywhere | Medium | Confirmed: temporal-runtime.ts has no validation hooks; plan G10 | Temporal and group-difference claims are unsupported (spec claim-to-validation table); 'never report raw distance alone' (plan A9) | M9/M10 | norm_policy = global_denominator ¦ per_time disclosed; VALIDATE() with seeded permutation + window bootstrap; p-values in model card | M | Yes
SENA-021 | All analytics execute client-side in the browser via vendored forks (vendor/jena-js, vendor/sna-js); no server-side source of truth for computed results | Medium | Confirmed: CONTEXT.md Runtime Boundaries; vendor/ tree | Numeric fidelity depends on unversioned forks; exports can't be recomputed server-side; limits dataset scale and auditability | Architecture | Extract analytics kernel as a versioned package; run compute server-side for exports/validation; pin + parity-test vendored libs against reference outputs | L | Partial (kernel extraction yes; full server compute can extend past week 12)
SENA-022 | Canvas coordinate clamping silently distorts even the exploratory geometry (scaleCoordinates clamps x,y into margins) | Low | Confirmed: lib/sena/layout.ts scaleCoordinates Math.max/Math.min clamp | Edge-of-canvas distances are wrong even for the layout view; invisible to users | UI | Scale-to-fit without clamping (already computes scale); if clamping retained, mark clipped points visually | S | Yes
SENA-023 | Enterprise store is a file-backed JSON (.sena-enterprise/enterprise-db.json) holding auth/team data, with uploads on local disk; PII risk if deployed as-is | Medium | Confirmed: CONTEXT.md Runtime Boundaries; .sena-enterprise/uploads in tree | Credentials/PII in a flat file inside the app directory; backup/exfil risk; not fit for real student data | Security / Infra | Use the existing Postgres adapter path for beta; encrypt uploads at rest; verify .gitignore excludes the store; document retention/deletion | M | Yes
Summary
Critical | 4
High | 10
Medium | 8
Low | 1
Total | 23

## Roadmap 12wk
SENA 12-Week Remediation Roadmap
v1.0 - 2026-07-07 - Compresses the development plan's P0-P5 (16 weeks) into 12 by deferring the items in the last row. Dependencies: each phase gates the next; golden tests are the contract between phases.
Phase | Weeks | Goal | Key tasks | Owner role needed | Risks | Exit criteria
P0 Foundations | 1-2 | Make change safe before making change | Repo audit + module map along M1-M11 seams; enterprise/ops change moratorium; A_SENA -> A_fusion naming sweep; typed data contract (dataset, config, provenance) in schema-registry; golden-test harness with worked-example fixture; T1-T4 encoded (expected-fail allowed, each red = ticket); CI pipeline gating PRs | Senior full-stack architect + junior dev (pairing) | Temptation to fix math while building harness (resist); hidden coupling in 10.9k-line workspace component slows audit | Harness runs T1-T4 in CI; data contract published; moratorium in effect; issue register triaged into tickets
P1 Correct core | 3-5 | The mathematical object becomes real and lawful | Layer builders per A1 (directed R preserved end-to-end; B count-vs-confidence declared; B_PC/B_CP ingest); ADMISSIBLE_NORMALIZE (max, frobenius, log1p_max; remove 'none'); fusion assembly + directed variant with tags; degrees/I0/V+ registry; Laplacian + three zero-degree conventions; directed operators (out/in RW, badged symmetrize); defaults alpha=beta=gamma=1 from config | Math-literate backend dev (lead) + junior dev | Symmetrization removal breaks existing views (mitigate: feature flag old path, badge it); normalization changes shift all edge weights (expected - explain to stakeholders) | T1-T9, T14, T15 green in CI; ingest test proves no silent symmetrization; provenance record emitted by every module
P2 Embedding truth | 6-8 | Person-code geometry becomes defensible | Embedding service: Laplacian eigenmaps, classical MDS + Schoenberg check, commute-time (dense pseudoinverse, cached); stress/strain + metric_exact in provenance; fusion view v2 renders Z = Phi(A_fusion); two-ring/ENA-overlay demoted to 'Exploratory layout' with badge; metric badge UI (operator, delta, d, seed, exact/stress) | Backend dev + senior architect (numerics review); UI dev for canvas swap | JS eigensolver numerics vs golden tolerances (fallback: server-side Python operator service); user pushback on changed layout (mitigate: keep overlay as named option) | T10-T11 green; workspace coordinates hash-match embedding output; badges render in e2e tests
P3 Attribution + typed measures | 9-10 | Say only what the evidence supports | Attribution service per A7 (G_i = X^T diag(Y_i) X, G_hat 0/0->0) + identity tests; wording gate (association vs contribution keyed to X_ita presence); typed centrality four families replacing/relabeling invented metrics; temporal norm_policy disclosure; model card generator v1 wired to provenance; render-block on incomplete card | Backend dev + UI dev; PhD reviewer signs wording rules | Wording gate touches many strings (centralize string builders first); G rework changes heatmaps users know | T12-T13 green; no mixed-type ranked list without tags (contract test); model card on every export; wording gate unit-tested
P4 Validation + hardening | 11-12 | Claims get tests; the site gets trust | VALIDATE() with seeded permutation (group labels, speaker labels) + window bootstrap; p-values + seeds in model card; UI badge catalog complete; method/platform copy rewritten to spec language; real Privacy/Terms/Security pages; gate /api/ena/run; Postgres store for beta; beta with one real (pseudonymized, consented) CSCL dataset; deployment checklist | Full team + founder for copy/legal; QA pass | Beta dataset consent/ethics lead time (start paperwork in P1); permutation runtime on real data (background jobs via existing ops/jobs queue) | All 15 golden tests green in CI on main; beta session end-to-end with model-carded exports; policy pages live; p-values reproducible by seed
Deferred (explicitly out of 12 weeks) | 13-16 | Scope protection | Full 47-check verification suite automation; Nystrom/sparse L+ path (N > ~3000); diffusion distance; in-degree operator variants beyond baseline; SCIM/enterprise surface un-freeze; report-generator polish; multi-language UI | - | Deferring these is the price of hitting week 12; revisit at P4 exit review | Deferral list reviewed and re-prioritized at week 12 retro

## Test Matrix
SENA Golden Test Matrix
v1.0 - 2026-07-07 - T1-T15 from the development plan section 6 (normative). S1-S9 supporting suites from the advisory test strategy. Status column to be updated by the team.
ID | Asserts | Expected / tolerance | Module | CI stage | Status (2026-07-07)
T1 | A_fusion equals the 6x6 exact-fraction matrix from the spec | max ¦A - expected¦ < 1e-12 | M4 Fusion | PR | Not implemented
T2 | Typed degrees | d = (2, 2.25, 1.25, 2, 8/3, 7/3) | M5 Operators | PR | Not implemented
T3 | Laplacian spectrum, PSD, one zero eigenvalue | {0, 0.88, 1.88, 2.61, 3.31, 3.81} (2 dp) | M5 Operators | PR | Not implemented
T4 | P3 bridge-connected: social degree 1, fused degree 1.25, P3 not in I0 | exact | M5 Operators | PR | Not implemented
T5 | Never-used code c4: d=0, retained in I0, L PSD, exactly 2 zero eigenvalues | exact | M5 Operators | PR | Not implemented
T6 | Zero-inverse convention: eig(L_sym) within [0, 2] | bounds hold | M5 Operators | PR | Not implemented
T7 | Epsilon convention: row of I - D_eps^-1 A at c4 -> identity row as eps -> 0+ | limit behavior | M5 Operators | PR | Not implemented
T8 | Directed fixture: min eig of sym(D_out - A_dir) = -0.218 (undirected claims forbidden on A_dir) | -0.218 (3 dp) | M5 Operators | PR | Not implemented
T9 | P = D_out^-1 A row-stochastic on V+; spectral radius <= 1 | bounds hold | M5 Operators | PR | Not implemented
T10 | Schoenberg on shortest-path Delta: min eig(K) = -1.637 -> exact=false; rank-2 distortion 0.718; stress ~= 0.104 reported | 3 dp | M6 Embedding | Merge | Not implemented
T11 | Commute-time embedding exact: max ¦ ¦¦Z_u-Z_v¦¦^2 - c(u,v) ¦ < 1e-9, all 9 person-code pairs (exclude u=v in the checker) | < 1e-9 | M6 Embedding | Merge | Not implemented
T12 | G slices PSD; sum_i G_i = X^T diag(P) X; window-normalized Y -> offdiag equals W | identities | M7 Attribution | PR | Not implemented
T13 | G_hat bounds: <= max_t X_ta X_tb; binary X -> [0,1]; zero-participation row -> 0 | bounds hold | M7 Attribution | PR | Not implemented
T14 | ADMISSIBLE_NORMALIZE axioms: N(0)=0, dims, nonnegativity, symmetry, divisor > 0 | all axioms | M3 Normalization | PR | Not implemented
T15 | Scale invariance: (c_S S, alpha/c_S) leaves A_raw unchanged; log rule flagged non-invariant | exact | M3 Normalization | PR | Not implemented
S1 | Ingest directedness: buildSocialMatrix never symmetrizes unless direction=undirected declared; directedS != S on asymmetric fixture | behavioral | M1/M2 | PR | Not implemented
S2 | Normalization property tests (random matrices): all Def. 4 axioms per rule; scale invariance for max/frobenius | property-based | M3 | PR | Not implemented
S3 | B weighting rule: count-based vs confidence-weighted each reproduce declared fixture | behavioral | M2 | PR | Not implemented
S4 | API provenance envelope on every analysis response; JSON-schema validated; schemaVersion snapshots | contract | API/M11 | PR | Not implemented
S5 | UI provenance e2e: distance views badge-gated; overlay always badged; export blocked without complete model card | Playwright | M11/UI | Merge | Not implemented
S6 | Wording gate: 'contribution' strings only when X_ita registered; else association/exposure | unit on string builders | M7/M11 | PR | Not implemented
S7 | Validation reproducibility: same seed -> same p; calibration on known-null synthetic data | statistical | M10 | Nightly | Not implemented
S8 | Security smoke: /api/ena/run gated; analysis routes 401 unauthenticated; no PII in share URLs | security | API | Merge | Not implemented
S9 | Vendored-lib parity: jena-js / sna-js outputs match pinned reference outputs (rENA/sna) on fixture data | parity | vendor | Nightly | Not implemented

## Golden Fixture
Worked-Example Golden Fixture (self-verifying)
Source: 20260705_SENA_clean version.docx, Worked Example; independently recomputed 2026-07-07 (NumPy). Blue cells = inputs. A_fusion, degrees and checks are live formulas.
Layer weights (declared)
alpha | 1
beta | 1
gamma | 1
S (raw, persons P1-P3) |  |  |  |  | W (raw, codes c1-c3)
| 0 | 4 | 0 |  |  | 0 | 3 | 1
| 4 | 0 | 1 |  |  | 3 | 0 | 2
| 0 | 1 | 0 |  |  | 1 | 2 | 0
B (raw, persons x codes)
| 2 | 1 | 0
| 0 | 2 | 1
| 0 | 0 | 3
Divisors (max rule)
div S | 4
div W | 3
div B | 3
A_fusion (live formulas)
| P1 | P2 | P3 | c1 | c2 | c3 |  |  | degree (SUM) | expected | check
P1 | 0 | 1 | 0 | 0.66667 | 0.33333 | 0 |  |  | 2 | 2 | PASS
P2 | 1 | 0 | 0.25 | 0 | 0.66667 | 0.33333 |  |  | 2.25 | 2.25 | PASS
P3 | 0 | 0.25 | 0 | 0 | 0 | 1 |  |  | 1.25 | 1.25 | PASS
c1 | 0.66667 | 0 | 0 | 0 | 1 | 0.33333 |  |  | 2 | 2 | PASS
c2 | 0.33333 | 0.66667 | 0 | 1 | 0 | 0.66667 |  |  | 2.6667 | 2.6667 | PASS
c3 | 0 | 0.33333 | 1 | 0.33333 | 0.66667 | 0 |  |  | 2.3333 | 2.3333 | PASS
Symmetry check
max ¦A - A^T¦ | 0 | PASS (symmetric)
Reference constants (cannot be computed by spreadsheet formulas - verify in code)
Quantity | Expected
eig(L), L = D - A | {0, 0.88, 1.88, 2.61, 3.31, 3.81} (2 dp), PSD, one zero | [5 empty] | T3
min eig(K), shortest-path delta (length = 1/weight) | -1.637 (3 dp) -> Euclidean embedding impossible | [5 empty] | T10
rank-2 classical MDS max distortion / stress | 0.718 / ~0.104 (3 dp) | [5 empty] | T10
commute-time embedding exactness (u != v) | < 1e-9 (reproduced at ~1e-13) | [5 empty] | T11
directed fixture min eig of sym(D_out - A_dir) | -0.218 (plan-provided fixture) | [5 empty] | T8

## Definition of Done
Definition of Done - next proof-of-concept stage
v1.0 - 2026-07-07 - The site is ready for the next PoC stage when every row below is Verified. Rows 1-10 restate the advisory's minimum conditions; 11-12 add the spec's Cor. 2 and the ethics baseline.
ID | Condition | How verified | Status
DoD-1 | Every displayed quantity (coordinates, distances, centralities, deltas, heatmaps) is computed from A_fusion or A_fusion^dir under declared conventions | Trace each view to its provenance record; e2e test S5 | Open
DoD-2 | Every graph operator carries a declared convention (self-loops, zero-degree, directed handling) in provenance and model card | Provenance schema validation S4 | Open
DoD-3 | Every cross-type (person-code) distance display carries operator, delta, d, seed and metric_exact flag; stress/strain when approximate | Badge e2e + T10/T11 | Open
DoD-4 | The 15 golden tests pass in CI on every release; nightly runs the full 47-check verification suite | CI dashboards | Open
DoD-5 | No silent symmetrization: directed data preserved end-to-end; symmetrization is a declared, permanently badged choice | S1 + badge e2e | Open
DoD-6 | No silent deletion of isolated vertices: I0 registry populated, retained in reports, visible (dimmed) in views | T4/T5 + UI e2e | Open
DoD-7 | No mixed-type centrality ranking without type labels; four typed families exposed separately | Contract test (M8) | Open
DoD-8 | No attribution wording stronger than the evidence: association/exposure default; contribution only with person-specific evidence (X_ita) | Wording-gate test S6 | Open
DoD-9 | Model card (items 1-10) attached to every rendered figure, export and share link; rendering blocked when incomplete | Render-block e2e | Open
DoD-10 | Validation results (permutation/bootstrap p-values, CIs) reproducible from recorded seeds | S7 reproducibility | Open
DoD-11 | alpha, beta, gamma interpreted only relative to the declared normalization rule; disclosed together everywhere they appear | T14/T15 + card check | Open
DoD-12 | Legal/ethics baseline: real Privacy/Terms/Security pages live; /api/ena/run gated; datasets pseudonymized with consent metadata before real-data beta | Manual + S8 | Open