## READ ME
SENA Issue Register - Re-examination 2026-07-09 (v2.0)
Scope | Re-audit of the SENA workspace (sena-hk-template working tree of 9 July 2026, commit 2ba2c63 + ~400 uncommitted changes) against the normative 2026-07-05 specification and the SENA.HK Algorithm Development Plan. Companion to SENA_Senior_Architect_Advisory_Report_v2.0.docx.
Priorities | P0 = fix immediately; blocks credibility/safety of all other work. P1 = must be fixed within the 3-month window. P2 = fix if capacity allows.
Effort | S = up to 1 day. M = up to 1 week. L = more than 1 week.
Status | Open / Partially fixed / Fixed (unverified in prod). 'Fixed (unverified in prod)' means implemented locally but not deployed because the working tree is uncommitted (see R-01).
Sheets | 1. Issue Register (P0-P2, R-01..R-21) · 2. Prior Advisory Trace (6-7 Jul S-01..S-20 disposition) · 3. Golden Tests (T1-T15 status) · 4. 12-Week Roadmap · 5. Definition of Done
Verification anchors | Worked example reproduced exactly: degrees (2, 2.25, 1.25, 2, 2.667, 2.333); Laplacian spectrum {0, 0.88, 1.88, 2.61, 3.31, 3.81}; Schoenberg min eig(K) = -1.637; rank-2 MDS max distortion 0.718; commute-time exact < 1e-9. Counterexamples reproduced: sample-dataset fusion max ¦A - A^T¦ = 1.0 with MDS available; P4 (in-degree 3, out-degree 0) listed isolated; Jacobi unresolved off-diagonal energy 0.19/29.6/266.7 at n=15/30/60.

## Issue Register
ID | Issue | Severity | Status (9 Jul) | Evidence / source | Why it matters | Affected module | Recommended fix | Effort | Within 3 months | Roadmap phase | Verification / acceptance
R-01 | Entire 7-9 Jul remediation uncommitted (~400 files); live www.sena.hk serves the 3 Jul build; no CI pipeline or branch protection | P0 | Open | git status: 403 modified/untracked; last commit 2ba2c63 (3 Jul); live /privacy empty; live /api/sena/docs has no operator/model-card markers | One git mistake can destroy a week of spec-alignment work; every external reviewer, pilot user, or journal referee sees the old non-compliant engine; no gate prevents regression | Repo / deploy / process | Tag pre-advisory-0709; commit in reviewed slices; GitHub Actions 5-stage gate (lint, golden math, core suite, build, smoke); deploy; verify live markers | M | Yes | Phase 0 (wk 1-2) | CI green on main; live strip + /privacy visible; /api/sena/docs mentions model card
R-02 | Directed-by-default fusion fed to symmetric-only embeddings; Jacobi mirrors the matrix (undeclared symmetrization); badge says 'Directed input preserved' | P0 | Open | model.ts:60 default direction=directed; buildEmbeddingDiagnostics passes raw fusion; repro: sample dataset max¦A-A^T¦=1.0, mds.available=true, stress=0.298 | The flagship joint view renders geometry the spec explicitly forbids (silent symmetrization) while asserting the opposite; any directed dataset produces confidently mislabeled coordinates | lib/sena/operators.ts + model.ts (M5/M6) | Symmetry assertion in eigensolver (throw on asymmetric); direction branch in buildEmbeddingDiagnostics: directed operators per plan A5 or explicit badged A_sym=(A+A^T)/2 | M | Yes | Phase 0 (wk 1-2) | Asymmetric-input test throws; directed dataset shows collapse badge or directed operators; T8/T9 green
R-03 | Eigensolver caps at 100 rotations (mislabeled sweeps), no convergence check - silently wrong spectra/embeddings for n above ~15 | P0 | Open | operators.ts senaSymmetricEigenDecomposition; measured unresolved off-diagonal Frobenius energy: 0.19 (n=15), 29.58 (n=30), 266.65 (n=60, ~23% of total) | Every spectral number (Laplacian spectra, eigenmaps, commute-time, Schoenberg exactness, stress, PSD checks) is wrong at real classroom sizes with no error raised; golden fixtures (<=7 nodes) cannot catch it | lib/sena/operators.ts (M5/M6) | Cyclic Jacobi with true sweeps + residual tracking; converge to tol or throw into provenance; invariant tests (trace, Frobenius, orthogonality) at n=30/60; or adopt vetted numeric lib | M | Yes | Phase 0 (wk 1-2) | n=60: sum(eig^2) matches ¦¦A¦¦_F^2 to 1e-8; residual in diagnostics; non-convergence is an explicit UI error
R-04 | Any isolated vertex disables ALL formal embeddings instead of V+ restriction; a unit test encodes the wrong convention as intended | P1 | Open | model.ts:108-148; test 'marks formal embedding diagnostics unavailable when isolated vertices...'; spec convention (a) and plan A4 require V+ restriction | Real CSCL data nearly always has unused codes or silent participants, so the joint embedding - the product's core - degrades to the non-metric ring exactly on real data | lib/sena/model.ts (M6) | Compute on largest connected component of V+; dim I0 nodes at margin; disclose 'computed on V+, ¦I0¦=k' in strip and model card; fix the defaults test | M | Yes | Phase 1 (wk 3-5) | Golden+c4 renders joint embedding for 6 nodes with c4 dimmed and listed; no ring fallback
R-05 | Directed isolation judged on row sums only: in-degree-only vertices misclassified as isolated (and via R-04 kill embeddings) | P1 | Open | operators.ts findSenaIsolatedVertices; repro: P4 with in-degree 3 / out-degree 0 listed in I0 | A student who is addressed but never initiates is reported as isolated - factually wrong social claim about a person, plus collateral embedding loss | lib/sena/operators.ts (M5) | Directed isolation = (in+out)==0, declared; optionally label source-/sink-isolated distinctly; fixture with in-degree-only vertex | S | Yes | Phase 1 (wk 3-5) | P4 fixture not in I0; labeled in/out degrees; convention string in model card
R-06 | Silent layout fallback chain: selected operator -> MDS -> exploratory ring with no signal to canvas; guardrail/strip can mislabel rendered geometry | P1 | Open | fusion-layout.ts jointLayout + formalEmbeddingCoordinates; static guardrail text in workspace-right-inspector-column.tsx:147-151 | Users read distances from a ring layout believing it is a declared embedding - the exact trust failure the spec's badges exist to prevent | components/sena/workspace (M11) | computeFusionLayout returns {nodes, source, reason}; canvas badge + guardrail copy bind to source; suppress metric readouts on fallback | M | Yes | Phase 1 (wk 3-5) | Forced-fallback tests: badge always matches rendered source
R-07 | Provenance envelope and model card hardcode MDS as the embedding of record regardless of selected/rendered operator | P1 | Open | analysis-run.ts:116-121 (Phi/delta/d/stress from MDS); model-card.ts embedding-geometry evidence MDS-only; operator choice lives only in UI state | Exports and API responses certify a different operator than the one the user saw - a provenance integrity defect in the disclosure system itself | lib/sena/analysis-run.ts, model-card.ts (M11) | Promote rendered operator into build options (bind UI to options.Phi); envelope reports that operator's diagnostics + inventory of all three | S | Yes | Phase 1 (wk 3-5) | Select commute-time, export: envelope operator=commute-time with on-screen values
R-08 | Eager computation: all 3 embeddings x 2 models rebuilt on main thread per option change; O((n+m)^3) x6 per slider move | P1 | Open | use-sena-fusion-workspace-main-shell-props.ts:347,356 (useMemo); buildEmbeddingDiagnostics computes mds+eigenmaps+commute always | UI freezes at pilot sizes; wasted compute amplifies R-03 wrongness; sliders (alpha/beta/gamma) become unusable on real data | workspace runtime / model.ts (M6) | Compute only selected operator, lazily; memoize by (datasetContentHash, configHash, operator); web worker or server /embedding route; debounce sliders | M | Yes | Phase 1-2 (wk 3-8) | n+m=150 dataset: interactive slider response < 200 ms; embedding served from cache on repeat
R-09 | ENA-space mode places persons barycentrically into code/jENA space (spec Example 1 projection error) with copy that tolerates distance readings | P1 | Open | fusion-layout.ts enaSpaceLayout (weighted average x1.28 + index offsets); guardrail: 'report dimensions, variance... with any distance interpretation' | Cross-type distances in this mode come from no joint model; the spec names this the canonical invalid operation for SENA | components/sena/workspace (M11) | Rename 'ENA anchor view'; copy: person-code distances are not model distances; disable cross-type distance affordances in this mode | S | Yes | Phase 2 (wk 6-8) | Copy review; no UI element invites cross-type distance reading in this mode
R-10 | Test suite not clean: 1 red test in tree (dossier-export 5s timeout); platform-pinned native deps (rolldown/rollup darwin-arm64) break clean Linux runners | P1 | Open | vitest run lib/sena/__tests__/sena.test.ts (timeout); rolldown binding missing on linux-arm64 until manually installed | CI (R-01) cannot go green; red-test normalization erodes the team's signal that math regressions matter | test infra | Fix or properly extend the dossier test timeout; ensure npm ci resolves platform optional deps; tag live/rehearsal suites out of the merge gate | S | Yes | Phase 0 (wk 1-2) | Full core suite green on a clean Linux CI runner
R-11 | Live consent gap: registration requires Terms/Responsible-AI agreement while live footer links resolve to /#docs placeholders (pages exist locally, undeployed) | P1 | Open | Live www.sena.hk footer (9 Jul); local app/privacy, app/terms, app/security, app/responsible-ai present in working tree | Consent to nonexistent policies is a trust and research-ethics defect on a platform holding student discourse | deploy / content | Ship R-01 (pages deploy with it); wire footer links; version the consent copy | S | Yes | Phase 0 (wk 1-2) | Live footer opens real policy pages; registration references match
R-12 | Enterprise state remains file-backed JSON (.sena-enterprise, ~72 MB) holding uploads/transcripts; retention, deletion, and classification undocumented; go-live gates blocked | P1 | Open | enterprise/state.ts adapter 'file-backed-json'; 07-07 gate results (storage engine blocked); Postgres code + Neon tests exist but not cut over | Student discourse is personal data; PoC can proceed only with a written classification, retention and provable deletion; production claims are blocked meanwhile | persistence / governance | Write data classification + retention policy; implement verified deletion endpoint (uploads + snapshots + derived artifacts); plan Postgres cutover behind flag | L | Policy: Yes. Cutover: No | Phase 3-4 (policy wk 9-12) | Deletion test: imported dataset fully removed; policy doc linked from Privacy page
R-13 | Workspace fragmentation: 326 files in components/sena/workspace incl. ~40 near-empty *-prop-group.ts shims created to satisfy module-boundary tests | P2 | Open | Directory listing; e.g. workspace-right-inspector-layout-boundary-composition-field-prop-group.ts | Navigation and onboarding cost; mechanical boundary compliance hides real coupling | frontend architecture | Consolidate prop-groups into cohesive modules; rewrite boundary tests to assert dependency direction, not file count | L | No | Backlog | File count halved without boundary-test regression
R-14 | Static guardrail copy not bound to diagnostics (joint-mode text claims declared operators even when fallback ring renders) | P2 | Open | workspace-right-inspector-column.tsx:147-151 | Copy contradicts the screen in failure states - subsumed by R-06 plumbing but needs its own copy fix | UI copy (M11) | Bind guardrail strings to layout source + embedding availability | S | Yes | Phase 1 (wk 3-5) | No reachable state with contradicting copy (test-forced)
R-15 | Hand-maintained fact monoliths (api-evidence-notes.ts 69 KB, api-route-facts.ts 31 KB, review-packet.ts 74 KB) duplicate route/evidence metadata | P2 | Open | lib/sena file sizes; manual literals | Facts drift from routes; reviews certify stale claims | docs/facts generation | Generate facts from the route manifest + zod schemas at build time; keep prose-only notes manual | M | No | Backlog | Generated facts diff-tested against manifest in CI
R-16 | Commute-time uses dense pseudoinverse via full eigendecomposition with no size cap or approximation path | P2 | Open | operators.ts senaCommuteTimeEmbeddingDiagnostics; plan A6 notes sparse/Nystrom needed for large N | Browser lock-up and (pre-R-03-fix) wrong results at scale; blocks pilot datasets beyond ~150 nodes | operators.ts (M6 performance) | Size cap with declared switch to server job; truncated-spectrum approximation with declared error in provenance | M | Cap: Yes. Approx: No | Phase 2 (wk 6-8) | n+m=150 embeds < 2 s server-side; error disclosed when approximate
R-17 | Provenance strip shows Seed = 'deterministic' instead of numeric seed + stochastic flag (options.seed exists, = 0) | P2 | Open | runtime-provenance-panels.tsx:112 | Spec disclosure list requires seed; researchers copying model cards need the value | UI provenance (M11) | Show options.seed and a stochastic yes/no flag | S | Yes | Phase 1 (wk 3-5) | Strip shows 'seed: 0 (deterministic operator)'
R-18 | Temporal cross-window deltas shown without the declared normalization policy (global vs per-window denominators) | P2 | Open | temporal-runtime.ts fusion totals; spec temporal section requires declared policy | Per-window normalization hides magnitude changes; readers must know which comparison they are seeing | M9 / UI | Policy chip next to temporal deltas + policy into snapshot provenance | S | Yes | Phase 3 (wk 9-10) | Chip renders both policies correctly in tests
R-19 | normalization='none' representable through API buildOptions for analytical runs (flagged inadmissible but accepted) | P2 | Open | operators.ts normalizeSenaMatrix('none'); types.ts SenaNormalization union | An inadmissible rule reachable via API undermines the admissibility contract (Definition 4) | M3 / options | Reject 'none' in resolveOptions for analytical runs or gate behind an exploratory flag that badges end-to-end | S | Yes | Phase 1 (wk 3-5) | API request with none returns 400 (or badged exploratory run)
R-20 | Undirected ingest double-counts self-interactions into S diagonal; S self-loop convention implicit | P2 | Open | model.ts buildSocialMatrix mirror write when source==target | Violates the declared zero-diagonal convention silently; small but a correctness contract breach | M2 | Skip mirror write for self-ties; zero S diagonal per convention; report self-tie counts as node attributes | S | Yes | Phase 1 (wk 3-5) | Self-interaction fixture yields convention-conformant S
R-21 | X_ita (person-specific coding evidence) not first-class; contribution wording gate is a boolean rather than evidence-backed data | P2 | Open | attribution-wording.ts gate flag; no X_ita table in contract | Contribution claims could be enabled without machine-checkable evidence - the exact overstatement the spec guards against | contract (M1/M7) | Optional speaker-attributed coded-segment table; gate requires it or a declared attribution-rule object; audit trail to segments | M | Yes | Phase 3 (wk 9-10) | Contribution wording impossible without registered evidence (test)

## Prior Advisory Trace
Prior ID (6-7 Jul) | Prior finding | Disposition on 9 Jul re-audit | Successor issue
S-01/G3 | A_fusion assembled but analytically inert; fusion view = ring overlay; no embedding computed from A_fusion | Fixed in working tree (unverified in prod): joint layout defaults to A_fusion embeddings with operator picker + provenance strip; NOT deployed | R-01 (deploy), R-06 (fallbacks)
S-02/G4 | No Schoenberg check, commute-time, stress, or metric-exact flag anywhere | Fixed in working tree: operators.ts implements all three with diagnostics; T10/T11 green | R-02/R-03 (validity limits)
S-03/G7 | Directionality collapsed silently on ingest (undirectedSocial default true) | Partially fixed: ingest preserves direction (default directed, tested); BUT embeddings now silently symmetrize downstream | R-02 (P0)
S-04/G8 | Normalization without admissibility checks; alpha=0.72/beta=0.64/gamma=0.86 hardcoded | Fixed in working tree: admissible engine + divisors disclosed; defaults 1/1/1 declared relative to rule; T14/T15 green | R-19 (none reachable)
S-05/G6 | Isolated vertices handled ad hoc; no I0 registry or zero-degree conventions | Partially fixed: I0 registry + retention + zero-inverse/epsilon operators exist; but any I0 disables embeddings (no V+) and directed isolation wrong | R-04, R-05
S-06/G5 | G tensor without slice identities or normalized variant | Fixed in working tree: G_i identities, G-hat with 0/0->0, bounds; T12/T13 green; wording gate live | R-21 (X_ita)
S-07/G2 | No golden regression fixtures | Fixed in working tree: T1-T15 (+T1b) implemented and green locally; no CI to run them | R-01, R-10
S-08/G9 | Edge types implicit | Fixed: rho(e) PP/CC/PC(+CP directed) serialized on edges; typed centrality families + mixed-ranking ban | -
S-09/G10 | No statistical validation tooling surfaced | Largely present: seeded permutation+bootstrap+Holm engine and validation route; temporal nulls + 2 null models pending | Phase 3-4 items
S-10/G1 | A_SENA vs A_fusion naming drift | Fixed: consistent A_fusion across code/API/UI observed | -
S-11 | Model card absent | Fixed in working tree: 10-section card with render gate; blocks publication export; share links not yet gated | Phase 3 (share gate)
S-12 | 10,860-line SenaFusionWorkspace.tsx monolith | Refactored into 326 workspace files - now over-fragmented with prop-group shims | R-13
S-13 | Legal placeholder links on live site | Pages authored locally; live still placeholders (undeployed) | R-11
S-14 | API surface sprawl (60 endpoints) | Frozen via api-surface-moratorium.ts (additive-or-reviewed-only); decomposition seams M1-M11 declared | -
S-15 | Local JSON persistence w/ transcripts | Unchanged (file-backed-json); Postgres code exists, not cut over | R-12

## Golden Tests
Test | Plan definition | Status (9 Jul, local) | Location | Gap / note
T1 | A_fusion equals the 6x6 exact-fraction matrix | PASS | sena-golden-operators.test.ts | Also verified independently to 0 error
T1b | Explicit directed B_CP block (not silent transpose) | PASS | sena-golden-operators.test.ts | -
T2 | Degrees d = (2, 2.25, 1.25, 2, 8/3, 7/3) | PASS | sena-golden-operators.test.ts | Verified independently
T3 | eig(L) = {0, 0.88, 1.88, 2.61, 3.31, 3.81}, PSD, one zero | PASS | sena-golden-operators.test.ts | Verified independently
T4 | P3 social degree 1 but fused degree 1.25; not in I0 | PASS | sena-golden-operators.test.ts | -
T5 | Unused c4: d=0, L PSD, exactly 2 zero eigenvalues | PASS | sena-golden-operators.test.ts | Pipeline-level behavior contradicts (R-04)
T6 | Zero-inverse: eig(L_sym) within [0, 2] | PASS | sena-golden-operators.test.ts | -
T7 | Epsilon convention: c4 row -> identity as eps -> 0+ | PASS | sena-golden-operators.test.ts | -
T8 | Directed counterexample: min eig sym(D_out - A_dir) = -0.218 | PASS | sena-golden-operators.test.ts | Diagnostics exist but not wired into embedding path (R-02)
T9 | P = D_out^-1 A row-stochastic on V+; ¦eig¦ <= 1 | PASS | sena-golden-operators.test.ts | Same wiring gap (R-02)
T10 | Shortest-path Delta: min eig(K) = -1.637; rank-2 distortion 0.718; stress reported | PASS | sena-golden-operators.test.ts | -
T11 | Commute-time: ¦¦Z_u - Z_v¦¦^2 == C(u,v) < 1e-9 all pairs | PASS | sena-golden-operators.test.ts | -
T12 | G slices PSD; sum_i G_i == X^T diag(P) X; window-normalized recovers W | PASS | sena-golden-attribution.test.ts | -
T13 | G-hat bounds; binary X in [0,1]; zero-participation row -> 0 | PASS | sena-golden-attribution.test.ts | -
T14 | Admissible-normalization axioms (N(0)=0, dims, nonneg, symmetry, divisor>0) | PASS | sena-golden-operators.test.ts + defaults | -
T15 | Scale invariance c_S S, alpha/c_S; log rule flagged variant | PASS | sena-golden-operators.test.ts | -
NEW-A | Asymmetry guard: eigensolver throws on asymmetric input; directed embeddings badge or refuse | MISSING | to add (Phase 0) | Covers R-02
NEW-B | Convergence invariants at n=30/60 (trace, Frobenius, orthogonality, residual) | MISSING | to add (Phase 0) | Covers R-03
NEW-C | V+ restriction renders embedding with I0 reported (golden+c4); in-degree-only vertex not isolated | MISSING | to add (Phase 1) | Covers R-04/R-05
NEW-D | Fallback provenance: badge equals rendered source under forced fallbacks | MISSING | to add (Phase 1) | Covers R-06/R-07/R-14
NEW-E | End-to-end golden: POST worked example to /api/sena/analyze, assert full artifact | MISSING | to add (Phase 1) | Locks all layers together
CI | All of the above on every push before deploy | MISSING (no CI) | GitHub Actions (Phase 0) | Covers R-01

## 12-Week Roadmap
Phase | Weeks | Goal | Key tasks | Owner roles | Risks | Exit criteria | Issues closed
Phase 0 | 1-2 | Secure the work, stand up CI, fix P0 math | Tag + commit working tree in reviewed slices; GitHub Actions 5-stage gate; fix dossier-test timeout; clean-runner npm ci; F-2 convergent Jacobi + invariant tests; F-1 symmetry guard + directed branch/badge; deploy and verify live markers | TL + BE (CI/deploy), TL + MA (math review) | Hidden coupling in 400-file changeset; Vercel env drift (use preview deploy) | CI green on main; live site serves new build; asymmetric input throws; n=60 invariants pass; T1-T15 green in CI | R-01, R-02, R-03, R-10, R-11
Phase 1 | 3-5 | Correct conventions end-to-end (V+, directed, fallbacks) | V+ restriction + I0 panel; directed isolation convention; fallback provenance through layout->canvas->copy; rendered operator into options/envelope/card; reject 'none'; S self-tie convention; lazy single-operator compute + memoization + worker; new fixtures (golden+c4, P4, forced fallbacks) | TL (operators/model), FE (layout/badges), MA (convention sign-off) | V+ x directed corner cases (multi-component policy needed first) | Golden+c4 renders joint embedding with I0 panel; badge always matches rendered source; responsive at n+m=150 | R-04, R-05, R-06, R-07, R-14, R-17, R-19, R-20 (+R-08 start)
Phase 2 | 6-8 | Embedding service productization + updated fusion visualization | POST /api/sena/embedding cached by (datasetHash, configHash, operator); sparse/Lanczos k-eigenpairs; per-source Dijkstra; approximate commute-time with declared error; exactness/stress copy final; ENA-anchor rename; direction toggle (out/in/symmetrized badged) | BE (service/cache), TL (numerics), FE (view/toggle) | Approximation-error communication (keep exact path default below threshold) | T10/T11 green against service; cached reproducible responses; 150-node embed < 2 s; directed toggle correctly badged | R-08, R-09, R-16(cap)
Phase 3 | 9-10 | Attribution, typed centrality, temporal, model card v3 | X_ita optional table + evidence-backed contribution gate; G/G-hat persisted to export; per-family centrality scale notes; temporal policy chip + permutation-tested deltas; model card v3 (rendered operator, V+/I0, directed convention, reliability evidence); share links gated | TL + MA (attribution), FE (panels), BE (share gating) | Temporal nulls with small window counts (MA sets minimums) | Contribution wording impossible without evidence; ungated share refused; temporal claims show p-values with seeds | R-18, R-21 (+R-12 policy start)
Phase 4 | 11-12 | Validation suite, docs, beta with real CSCL data, hardening | Code-label shuffle + degree-preserving rewiring nulls; claim-to-validation table in reports; beta with real lesson-study dataset with PI; docs aligned to A_fusion language; verified deletion endpoint + retention doc; load test; error-state review | PI + TL (beta), FE (docs/UI), BE (hardening) | Beta findings reopen Phase 1 items (reserve 30% slack wk 12) | Definition of Done fully satisfied; beta signed by PI; tagged release deployed | R-12 (policy), residual P2s

## Definition of Done
# | Condition | Status 9 Jul | Verified by
1 | All displayed quantities computed from A_fusion or A_fusion^dir under declared conventions | Partial - joint path yes; directed path invalid (R-02); social metrics declared as S-block measures | Golden E2E test + provenance audit
2 | Declared conventions for every graph operator (self-loops, zero-degree, directed) | Partial - constants exist; V+ not enforced (R-04) | Convention tests + model card render
3 | Cross-type distance claims carry exactness or stress information | Partial - joint strip yes; fallback states dishonest (R-06) | Fallback provenance tests
4 | Golden tests T1-T15 passing in CI on every deploy | Blocked - tests pass locally; no CI (R-01) | CI pipeline (Phase 0)
5 | No silent symmetrization anywhere | Violated (R-02) | Asymmetry-guard tests
6 | No silent deletion of isolated nodes; I0 retained and reported | Partial - retained/reported; embedding disablement over-broad (R-04); directed misclassification (R-05) | V+/I0 tests + panel check
7 | No mixed-type centrality ranking without type labels | Satisfied | Existing defaults test
8 | No attribution wording stronger than the evidence | Satisfied at gate level; X_ita to become first-class (R-21) | Wording-gate tests
9 | Model card attached to every export/share view; incomplete cards block rendering | Partial - publication export gated; share links not yet | Share-gate test (Phase 3)
10 | Reproducible validation results with seeds (permutation, bootstrap, Holm) | Satisfied in inference engine; temporal nulls pending | Validation route tests
11 | Live site serves the audited build; legal/consent pages live | Violated (R-01, R-11) | Deploy verification checklist
12 | Numerics correct at pilot scale (n+m >= 60) with declared residuals | Violated (R-03) | n=30/60 invariant tests