## README
SENA — Senior-Architect Advisory Tracker
Companion workbook to SENA_Architecture_Advisory_Report.docx · 6 July 2026 · Confidential
Purpose | A working tracker for the SENA remediation. Filter, assign owners, and update status as the 12-week plan runs.
Normative basis | 20260705_SENA_clean version.docx (math spec) + SENA.HK Algorithm Development Plan. The July 5 spec is normative.
Evidence basis | Audited against the deployed source repo (sena-hk-template, Next.js on Vercel). File:line references are authoritative.
TABS
1 · Issue Register | 20 severity-ranked issues with evidence, module, fix, effort, and 3-month flag. Autofilter + owner/status columns.
2 · Golden Tests | T1–T15 regression fixtures bound to the worked example. The CI gate for every deploy.
3 · Roadmap | 12-week / 5-phase plan with goal, tasks, owner role, risks, exit criteria, and a week grid.
4 · Module Map | Target pipeline M1–M11 vs. what exists in the code today.
SEVERITY LEGEND
Critical | Blocks mathematical fidelity or reliable modification. Must fix.
High | Materially misleads or blocks maintainability. Fix within 3 months.
Medium | Important correctness/clarity gap. Schedule within the window.
Low | Lower urgency; fast-follow acceptable.
Effort key | S ≤ ~2 days · M ≤ ~1–2 weeks · L ≥ ~2–4 weeks or cross-cutting

## Issue Register
Prioritized Issue Register — 20 issues
ID | Issue | Severity | Evidence / source (file:line) | Why it matters | Affected module | Recommended fix | Effort | ≤3 mo | Owner | Status
S-01 | A_fusion assembled but never used for analytics | Critical | model.ts:608–629,:1027; degree(S):179; components(S):162; report.ts:176 | The headline object is decorative; nothing users see is fused. | M4/M5 | Route all displayed quantities through A_fusion; delete/demote the S-only path. | L | Yes |  | Open
S-02 | Fusion view is an ENA-projection overlay, not a joint embedding | Critical | layout.ts (source:'jena-js'; points/nodePositions) | Person–code distance is not a modelled quantity (spec Example 1). | M6 | EMBED(A_fusion) via a declared operator; overlay = exploratory only. | L | Yes |  | Open
S-03 | No graph-operator layer (Laplacian / eigen) | Critical | repo-wide: 0 non-test files for Laplacian/eigen/commute/Schoenberg | Corollary 1, Props 4–5 and half the golden tests are impossible. | M5 | Build a typed operators module + eigensolver. | L | Yes |  | Open
S-04 | No metric-validity / stress reporting | Critical | no Schoenberg/MDS/commute; 'strain' hits are 'constraints' substrings | Cross-type distances shown with no exactness or stress. | M6 | SCHOENBERG_MDS + COMMUTE_TIME_EMBED + stress/strain readout. | M | Yes |  | Open
S-05 | No golden-test harness for the worked example | Critical | package.json has no math/golden script; tests are route/ops only | Math can regress silently; refactors are unverifiable. | M0 | Encode the worked-example fixture; T1–T15 in CI. | M | Yes |  | Open
S-06 | Silent symmetrization of directed social data | High | report.ts:133,:187; symmetric bridge model.ts:618–619 | Direction dropped w/o disclosure; A_fusion^dir impossible. | M1/M2/M5 | Preserve R directed; badge symmetrization; add directed assembly + operators. | L | Yes |  | Open
S-07 | Normalization lacks admissibility checks & Frobenius | High | model.ts:65–73 (max/log-max/none only) | No axioms enforced; α/β/γ uninterpretable vs the rule. | M3 | ADMISSIBLE_NORMALIZE with axiom asserts + provenance; add Frobenius. | M | Yes |  | Open
S-08 | Isolated nodes judged on S block, not A_fusion | High | components(S) model.ts:162; socialComponent:473 | P3-type nodes mis-marked isolated; no I0 registry. | M5 | Compute I0 on A_fusion; retain & report; V+/zero-inverse/eps conventions. | M | Yes |  | Open
S-09 | Attribution overstated; G='contribution', no G_hat | High | CONTEXT.md; visual-grammar 'contribution arcs'; no Ghat in code | Overstates person-level evidence (spec Example 4). | M7 | Default 'association'; add G_hat; gate 'contribution' on X_ita. | M | Yes |  | Open
S-10 | No render-blocking model card | High | 0 modelCard files; provenance exists but is unenforced | Unfaithful/undisclosed figures can render and be exported. | M11 | Model-card generator + block_render_if_missing gate. | M | Yes |  | Open
S-11 | Validation null models are generic mean-shuffles | High | inference.ts:183–195 (label shuffle + bootstrap of means) | Not structure-preserving; group/temporal claims under-supported. | M10 | Add degree-preserving rewiring, code-label & stanza shuffles, bipartite null, sensitivity. | M | Yes |  | Open
S-12 | Degrees are social-only, not fused typed degrees | High | degree(S) model.ts:179; socialDegree:470 | Node emphasis contradicts the fused model (T2). | M5 | Compute typed degree from A_fusion. | S | Yes |  | Open
S-13 | Typed centrality not four separated families | Medium | sna.js betweenness on S block report.ts:176; bridge ranking:214 | Risk of mixed-type ranking; no scale disclosure. | M8 | Compute four families; tag whole-graph; block mixed lists in UI. | M | Yes |  | Open
S-14 | Temporal uses per-time normalization only | Medium | model.ts:754–764 normalizeTemporalWindows | Hides magnitude change; no declared policy. | M9 | Assemble A(t) under a declared policy; ΔA distances + significance. | M | Yes |  | Open
S-15 | Architecture inversion: ~90 ops files vs thin math core | High | lib/sena/enterprise/* + ops-*; math in a handful of files | Effort & code gravity in the wrong tier; math is hard to modify. | All | Freeze enterprise growth; consolidate math into tested services. | L | Partial |  | Open
S-16 | Math split across vendor bundles + UI-adjacent code | Medium | jena-js, sna.js vendored; fusion in model.ts; interp in report.ts | No single source of truth for 'what SENA computes'. | All | Centralize analytics behind /api services; vendor libs = within-type only. | L | Partial |  | Open
S-17 | Person ID ambiguity | Medium | layout.ts probes personId/person/unit/unitId/id | Fragile joins; mis-placed nodes. | M1 | Enforce one canonical, stable personId. | S | Yes |  | Open
S-18 | No codebook versioning / edge→source audit trail | Medium | no codebookVersion on codes; no edge provenance to source records | Mixed codebooks corrupt W/B; no traceability. | M1 | Version codebooks; link every edge to source segments. | M | Yes |  | Open
S-19 | De-identification not enforced for discourse data | High | .sena-enterprise file store; no PII redaction at ingest | Student PII risk; discourse may involve minors. | Security | PII redaction + pseudonymous IDs by default; encrypt at rest; retention policy. | M | Yes |  | Open
S-20 | Eigen/commute compute has no scale plan | Low | operators absent, so no sparse/approx path yet | Latency regression risk on real datasets. | Perf | Sparse + Nyström past a measured threshold; cache artifacts. | M | Partial |  | Open
Summary (live) |  |  | Critical | 5 | High | 9 |  | Must-do ≤3mo | 17 | 20 total
|  |  | Medium | 5 | Low | 1

## Golden Tests
Golden Regression Tests (worked example) — CI gate for every deploy
Fixture: S=[[0,4,0],[4,0,1],[0,1,0]] W=[[0,3,1],[3,0,2],[1,2,0]] B=[[2,1,0],[0,2,1],[0,0,3]] · norm=max · α=β=γ=1
Test | Asserts (target numbers fixed by the spec) | Module | Phase | CI gate | Status
T1 A_fusion | Exact 6×6 fused matrix (fractions printed in the spec). | M4 | Wk1–2 | Yes | Not built
T2 Degrees | d = (2, 2.25, 1.25, 2, 2.667, 2.333) computed from A_fusion. | M5 | Wk3–5 | Yes | Not built
T3 Laplacian spectrum | eig(L) = {0, 0.88, 1.88, 2.61, 3.31, 3.81}; PSD; exactly one zero. | M5 | Wk3–5 | Yes | Not built
T4 Bridge keeps P3 | P3 social degree 1 but fused degree 1.25; P3 ∉ I0. | M5 | Wk3–5 | Yes | Not built
T5 Unused code | add c4: d(c4)=0; L still PSD; exactly two zero eigenvalues. | M5 | Wk3–5 | Yes | Not built
T6 zero-inverse | eig(L_sym) ⊆ [0, 2]. | M5 | Wk3–5 | Yes | Not built
T7 eps-convention | row of I − D_eps⁻¹A at c4 → identity row as eps → 0⁺. | M5 | Wk3–5 | Yes | Not built
T8 directed indefinite | min eig sym(D_out − A_dir) = −0.218 < 0 (detected & flagged). | M5 | Wk3–5 | Yes | Not built
T9 row-stochastic | P = D_out⁻¹A row-stochastic on V+; max¦eig(P)¦ ≤ 1. | M5 | Wk3–5 | Yes | Not built
T10 Schoenberg/MDS | min eig(K) = −1.637 ⇒ exact=false; rank-2 MDS max distortion 0.718; stress reported. | M6 | Wk6–8 | Yes | Not built
T11 commute-time | max ¦ ‖Z_u−Z_v‖² − C(u,v) ¦ < 1e-9 on all 9 person–code pairs. | M6 | Wk6–8 | Yes | Not built
T12 G slices | G_i PSD; Σ_i G_i = Xᵀ diag(P) X; window-normalized Y ⇒ offdiag = W. | M7 | Wk9–10 | Yes | Not built
T13 G_hat bounds | G_hat ≤ max_t X_ta·X_tb; binary X ∈ [0,1]; zero-participation row → 0. | M7 | Wk9–10 | Yes | Not built
T14 normalization axioms | N(0)=0; dims preserved; nonneg; symmetry preserved; divisor > 0. | M3 | Wk3–5 | Yes | Not built
T15 scale invariance | max/frob invariant to layer rescale; log rule flagged as variant. | M3 | Wk3–5 | Yes | Not built
Green in CI | 0 / 15 passing
Gate rule | Fail-closed: any red golden test blocks release. Seeds fixed & recorded so permutation/bootstrap p-values reproduce.

## Roadmap
12-Week Remediation Roadmap — 5 phases
Phase | Weeks | Goal | Key tasks | Owner role | Risks | Exit criteria
P0 Foundation | 1–2 | Make the math testable & consistently named. | Golden-test harness (T1–T15 scaffold); worked-example fixture; typed data contract; finish A_SENA→A_fusion naming sweep; CI fail-closed. | Senior/full-stack + math reviewer | Team underestimates harness value and defers it. | T1–T4 green or precisely ticketed; data-contract schema merged; CI blocks on golden tests.
P1 Core engine | 3–5 | Faithful layers, normalization, fusion, operators, direction. | M2 layer builders (directed variants); M3 admissible-normalization (+Frobenius, axiom asserts, provenance); M4 A_fusion/A_fusion^dir; M5 degrees/Laplacian/normalized operators w/ zero-degree conventions; isolated-node retention. | Backend engineer + numerics reviewer | Numerics correctness; reconciling golden numbers. | T1–T9, T14–T15 green; all degrees/components from A_fusion; no silent symmetrization.
P2 Embedding | 6–8 | Real joint geometry with honest distortion. | M6 embedding: Laplacian eigenmaps, classical MDS + Schoenberg check, commute-time; stress/strain readout; replace ring-overlay analytical reading with EMBED(A_fusion). | Numerics engineer + frontend | Pseudoinverse/eigensolver cost; Schoenberg iff subtlety. | T10–T11 green; fusion view runs off A_fusion; distances carry exact/stress metadata.
P3 Attribution/typed | 9–10 | Correct attribution, typed centrality, temporal, model-card proto. | M7 G/G_hat with wording gate; M8 four typed-centrality families; M9 temporal deltas under declared policy; first model-card generator (items 1–10). | Backend + product/UX | Wording rules skipped under time pressure. | T12–T13 green; 'contribution' gated on X_ita; model card renders for one E2E view.
P4 Validation/UX/harden | 11–12 | Enforce disclosure, validate claims, beta on real data. | M10 structure-preserving null models + sensitivity; UI badges + isolated-node/direction toggles; model-card render-gate; docs; CSCL beta; perf pass (sparse L⁺). | Full team + pilot researcher | Schedule crunch: validation + UI + docs + beta collide. | Model card blocks incomplete renders; p-values reproducible by seed; all 15 golden tests green; sign-off vs July 5 spec.
Week grid (module activity)
Module | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
M0 Harness
M2 Layers
M3 Normalize
M4 Fusion
M5 Operators
M6 Embedding
M7 Attribution
M8 Centrality
M9 Temporal
M10 Validation
M11 Model card/UI

## Module Map
Target Pipeline (M1–M11) vs. Current Code
Module | Target responsibility | State today | Assessment
M1 Ingest | events, windows, coding; directed R preserved | import.ts / import-adapters.ts; direction collapsed on ingest | Partial
M2 Layer builders | R,X,Y → S,W,B (+directed) | model.ts builds S,W,B,G; bridge hard-coded symmetric | Partial
M3 Normalization | admissible rules + axioms | inline model.ts (max/log-max/none); no engine/asserts | Weak
M4 Fusion assembly | A_fusion / A_fusion^dir / A_fusion(t) | correct block build model.ts:608–629; consistent naming | Good
M5 Graph operators | degrees, I0, L, L_sym, L_rw | ABSENT — no Laplacian/degree-on-fusion/normalized ops | Missing
M6 Embedding | eigenmaps / MDS+Schoenberg / commute-time | ABSENT as joint embedding; layout reads jena-js ENA projection | Missing
M7 Attribution | G and G_hat with wording rules | G present as 'contribution'; no G_hat; no slice identities | Weak
M8 Typed centrality | four separated families | sna.js betweenness on S + bridge ranking | Partial
M9 Temporal | A(t) deltas under declared policy | temporal-runtime.ts; per-time normalization only | Partial
M10 Validation | null models, permutation, bootstrap | inference.ts: seeded permutation+bootstrap+Holm; generic null | Partial — strong base
M11 Reporting/UI | model card, badges, panels | rich report.ts + workspace; no render-blocking model card | Partial